## Resource Allocation Matrix
Resource Allocation Matrix - CRM Delivery
Resource Name | Role | Project | Sprint / Week | Task / Activity | Allocation % (Weekly) | Planned Effort (hrs) | Actual Effort (hrs) | Utilization Status | Remarks
Resource A | CRM Analyst | CRM Delivery | Sprint 1 | Lead & opportunity workflow setup | 80% | 32 | 34 | Overutilized | Slight effort overrun due to requirement clarifications
Resource B | Support Executive | CRM Delivery | Sprint 2 | Customer onboarding support | 60% | 24 | 22 | Optimal | On track
Resource C | QA Analyst | CRM Delivery | Sprint 3 | UAT testing for CRM workflows | 50% | 20 | 18 | Underutilized | Available capacity in next sprint
Resource D | PMO Support | CRM Delivery | Sprint 4 | Status reporting & coordination | 40% | 16 | 16 | Optimal | On track
Resource E | CRM Analyst | CRM Delivery | Sprint 5 | Data validation & reporting checks | 70% | 28 | 30 | Overutilized | Additional rework identified during testing