## Weekly Project Status Report
Weekly Project Status Report
Project Name | Agile Project Coordination – SaaS Feature Delivery | Project Code | - | Status Key | Budget Key
Project Manager | Project Manager – Internal Simulation | Date of Status Entry | 2024-07-05 | ROADBLOCK / OVERAGE | OVER
Period Covered | 01 July 2024 – 05 July 2024 | Projected Date of Completion | 2024-09-30 | POTENTIAL RISKS / DELAYS | ON
|  |  |  | ON TRACK | UNDER
Project Status This Week
Overall Project Status | ON TRACK | Summary | Project activities progressed as planned. Sprint tasks remained on schedule with no critical risks, and coordination between development and QA ensured timely updates.
Milestones | Sprint planning completed – Scope finalized and approved by stakeholders.
Feature development in progress – Tasks progressing as per sprint plan with no blockers.
QA preparation initiated – Test cases reviewed and aligned with development timelines.
Project Components
Component | Status | Owner / Team | Notes
Budget | UNDER | PMO | Budget not actively tracked for internal simulation project.
Resources | POTENTIAL RISKS / DELAYS | QA / Engineering | QA availability dependent on completion of development tasks.
Timeline | ON TRACK | Delivery Team | Delivery progressing as per sprint plan with no current delays.
Scope | ON TRACK | Product / PMO | Scope finalized and no changes introduced this period.
Work Accomplished
Task No. | Description | Owner / Team | Reception
1 | Sprint planning meeting conducted and sprint backlog finalized with stakeholders. | Product / Engineering | Completed
2 | Tracked sprint tasks and updated progress in Jira to ensure visibility across teams. | Project Coordination / PMO | Completed as planned
3 | Tracked sprint tasks and updated progress in Jira to ensure visibility across teams. | QA Team | In progress
Risks And Roadblocks
Risk No. | Description | Owner / Team | Fix
R1 | Delay in QA availability may impact UAT timelines. | QA Team | Coordinating with development team to align task completion and QA availability.
R2 | Dependency on development task completion could affect QA start. | Engineering / QA | Monitoring progress closely and escalating if delays arise.
Upcoming Work
Owner | Status | Update / Insight
Development Team | In Progress | Continue feature development as per sprint plan and address any pending tasks. | Coordinating with development team to align task completion and QA availability.
QA Team | Planned | Begin QA execution once development tasks are completed and validated. | Monitoring progress closely and escalating if delays arise.
Product Owner | Upcoming | Review completed features and provide feedback for UAT readiness. | Monitoring progress closely and escalating if delays arise.
Project Coordinator | Planned | Prepare next week’s status report and coordinate stakeholder updates. | Monitoring progress closely and escalating if delays arise.