## Sheet1
Sprint | Task ID | Task Name | Module | Owner | Status | Planned Effort (hrs) | Actual Effort (hrs) | Start Date | End Date | Risk | Dependency | PMO Remarks
Sprint 3 | T-101 | Lead & Opportunity workflow setup | CRM | CRM Analyst | Completed | 16 | 18 | 2026-01-15 | 2026-01-21 | No | None | Minor rework after stakeholder review
Sprint 3 | T-102 | Customer onboarding data setup | CRM | Support Executive | In Progress | 20 | 14 | 2026-01-17 | 2026-01-25 | Yes | Business | Awaiting validation from business team
Sprint 3 | T-103 | UAT testing for CRM workflows | QA | QA Analyst | In Progress | 12 | 10 | 2026-01-18 | 2026-01-26 | No | None | Test execution ongoing
Sprint 3 | T-104 | Sprint status reporting & coordination | PMO | PMO Support | Completed | 8 | 8 | 2026-01-15 | 2026-01-21 | No | None | Weekly status shared with stakeholders
Sprint 3 | T-105 | CRM dashboard requirement review | Reporting | CRM Analyst | Blocked | 10 | 4 | 2026-01-20 | 2026-01-27 | Yes | Business | Pending stakeholder sign-off