## Sheet1
Risk / Blocker ID | Risk / Blocker Description | Category | Impact | Likelihood | Owner | Status | Mitigation / Action Plan | Target Resolution Sprint
R-01 | Pending business validation on CRM onboarding workflow | Dependency | High | Medium | CRM Analyst | Open | Follow up with business stakeholders and schedule validation review | Sprint 4
R-02 | Resource overutilization for CRM Analyst | Resource | Medium | Medium | PMO Support | Monitoring | Redistribute workload and review allocation matrix | Sprint 4
R-03 | UAT feedback delays impacting release readiness | Delivery | High | Low | QA Analyst | Open | Prioritize UAT scenarios and align test cycles | Sprint 3
R-04 | Incomplete data migration affecting reporting accuracy | Data | Medium | Low | Support Executive | Closed | Data validation completed and approved | Sprint 3