## RISKS
RISKS
No. | Task | Impact | Start Date | End Date | Duration in days | RAID Category | Impact | Status | Owner
R-01 | Limited QA availability during sprint end | May delay UAT execution and defect validation timelines | 2024-07-01 | 2024-07-12 | 12 | Risk | Risk | In Progress | QA Lead
R-02 | Dependency on completion of core feature before UAT | UAT start date dependent on timely development sign-off | 2024-07-03 | 2024-07-10 | 8 | Risk | Dependency | On-Track | Development Team
R-03 | Minor requirement clarifications pending from stakeholders | Minor requirement clarifications pending from stakeholders | 2024-07-02 | 2024-07-05 | 4 | Risk | Assumption | Resolved | Product Owner

## ASSUMPTIONS
ASSUMPTIONS
No. | Task | Impact | Start Date | End Date | Duration in days | RAID Category | Impact | Status | Owner
A-01 | Sprint scope will remain unchanged during execution | Unplanned scope changes may affect delivery timelines | 2024-07-01 | 2024-07-05 | 5 | Assumption | Moderate | On-Track | Product Owner
A-02 | Stakeholders will be available for reviews and approvals | Delayed feedback may impact UAT and release timelines | 2024-07-02 | 2024-07-09 | 8 | Assumption | High | In Progress | Project Manager
A-03 | Test environment will be ready before UAT start | UAT execution depends on environment stability | 2024-07-03 | 2024-07-10 | 8 | Assumption | Critical | Resolved | QA Team

## ISSUES
ISSUES
No. | Task | Impact | Start Date | End Date | Duration in days | RAID Category | Impact | Status | Owner
I-01 | QA start delayed due to incomplete development tasks | UAT start pushed, requiring sprint plan adjustment | 2024-07-04 | 2024-07-06 | 3 | Issue | High | Resolved | Development Team
I-02 | Gaps identified in test case coverage during QA review | Risk of missing functional validation during UAT | 2024-07-05 | 2024-07-07 | 3 | Issue | Moderate | In Progress | QA Team
I-03 | Delay in stakeholder feedback on feature review | Approval pending, blocking UAT sign-off | 2024-07-06 | 2024-07-09 | 4 | Issue | High | Needs Review | Product Owner

## DEPENDENCIES
DEPENDENCIES
No. | Task | Impact | Start Date | End Date | Duration in days | RAID Category | Impact | Status | Owner
D-01 | UAT execution dependent on completion of development tasks | Any delay in development will impact UAT start timeline | 2024-07-03 | 2024-07-10 | 8 | Dependency | Dependency | On-Track | Development Team
D-02 | Test case finalization dependent on approved requirements | Delayed approvals may impact QA preparation schedul | 2024-07-02 | 2024-07-06 | 5 | Dependency | Dependency | In Progress | Business Analyst/QA Team
D-03 | Release readiness dependent on stakeholder UAT approval | Go-live decision pending business sign-off | 2024-07-07 | 2024-07-12 | 6 | Dependency | Dependency | Needs Review | Product Owner/Business Stakholders

## Dropdown Keys
DROPDOWN KEYS
RAID Category | Impact | Status
Risk | Negligible | Open
Assumption | Low | In Progress
Issue | Moderate | Ongoing
Dependency | High | On-Track
| Critical | Needs Review
Approved
Overdue
On Hold
Resolved
Closed